## Slide 1
Kế hoạch Phát triển
Ứng dụng Quản lý Dự án Flutter
Tương tự monday.com - Tối ưu cho Mobile
16 tuần
3 developers
$15K-25K
Manus AI - Project Planning & Architecture Design
Ngày: 18/06/2025

## Slide 2
Tổng quan Dự án
Mục tiêu
Ứng dụng quản lý dự án mobile-first
Trải nghiệm người dùng mượt mà
Cộng tác nhóm real-time
Kiến trúc có thể mở rộng
Platform
iOS
Android
Flutter
16
Tuần
3
Developers
Ngân sách
Development
$34,000
Infrastructure
$5,400
Other costs
$2,700
Total
$42,100

## Slide 3
Phân tích Thị trường
Monday.com - Top 10 Features
Customizable Dashboards
Visual Project Tracking
Automation
Collaboration Tools
Time Tracking
200+ Integrations
Competitive Advantage
Mobile-first Design
Flutter Performance
Vietnamese Localization
Cost-effective Solution
Market Opportunity
📈
Growing Remote Work
📱
Mobile-first Trend
🇻🇳
Vietnamese Market
💡
SME Focus

## Slide 4
Tính năng Cốt lõi
Authentication
• Đăng ký/Đăng nhập
• Profile management
• Team invitation
• Role management
Project Management
• Create/Edit/Delete
• Project overview
• Search & filter
• Team members
Task Management
• Kanban board
• Drag & drop
• Task details
• Priority levels
Collaboration
• Real-time comments
• @Mentions
• File attachments
• Activity feed
Dashboard
• Project overview
• Task statistics
• Progress tracking
• Recent activities
Future Features
• Time tracking
• Gantt charts
• Custom fields
• Integrations
MVP Strategy
Tập trung vào 5 tính năng cốt lõi để đảm bảo chất lượng và trải nghiệm người dùng tốt nhất

## Slide 5
Thiết kế UI/UX
Design System
Colors
Typography
Roboto Bold
Roboto Medium
Roboto Regular
Spacing
4dp • 8dp • 16dp • 24dp • 32dp
Border Radius: 8dp
Touch Target: 44dp min
Dashboard
Kanban Board
Task Detail
Design Principles
Mobile-First
Tối ưu cho mobile
Intuitive
Dễ hiểu và sử dụng
Consistent
Nhất quán toàn bộ app
Accessible
Hỗ trợ accessibility

## Slide 6
Kiến trúc Kỹ thuật
Frontend
• Flutter 3.24.5
• Dart 3.5.4
• Riverpod (State)
• Go Router (Navigation)
• Material Design 3
Backend
• FastAPI (Python)
• PostgreSQL
• JWT Authentication
• RESTful API
• WebSocket (Real-time)
Clean Architecture
Presentation Layer
Pages, Providers, Widgets
Domain Layer
Entities, Use Cases, Repositories
Data Layer
Models, Data Sources, APIs
Technology Stack
Flutter
Riverpod
Hive
Dio
FastAPI
PostgreSQL
AWS/GCP
JWT Auth
Key Benefits
Performance
Flutter native performance
Scalable
Clean Architecture
Cross-platform
iOS & Android
Maintainable
Modular structure

## Slide 7
Timeline Phát triển
16 tuần - 5 phases chính
Phase 1: Foundation Setup
Tuần 1-2
Environment & Infrastructure
• Flutter project setup
• Clean Architecture
• Backend API setup
• Authentication system
Phase 2: Core Features
Tuần 3-8
Auth, Projects, Tasks
• User management
• Project CRUD
• Task management
• Basic UI components
Phase 3: Advanced Task Management
Tuần 9-12
Kanban & Collaboration
• Kanban board
• Drag & drop
• Real-time comments
• File attachments
Phase 4: Dashboard & Analytics
Tuần 13-14
Analytics & Reporting
• Project overview
• Task statistics
• Progress tracking
• Search & filter
Phase 5: Polish & Deployment
Tuần 15-16
Testing & Launch
• UI/UX polish
• Performance optimization
• Testing & QA
• App store deployment

## Slide 8
Nhóm phát triển & Ngân sách
Team Structure
Flutter Developer (Senior)
Frontend development, UI implementation
3+ years Flutter experience
Backend Developer (Mid-Senior)
API development, database, deployment
3+ years Python/FastAPI experience
UI/UX Designer (Part-time)
Design system, wireframes, user testing
Mobile app design experience
Budget Breakdown
Development
$34,000
Infrastructure
$5,400
Other costs
$2,700
Total Budget
$42,100
Cost Optimization Options
Junior Developers
Save $8,000
Self-hosted
Save $3,000
Minimal Services
Save $500
Optimized Total: $30,600

## Slide 9
Quản lý Rủi ro
Technical Risks
Flutter Performance
Low-end devices compatibility
Medium
Mitigation: Early testing, optimization
Real-time Features
WebSocket implementation complexity
Medium
Mitigation: Prototype early, fallback options
File Storage Costs
Unexpected storage expenses
Low
Mitigation: Size limits, monitoring
Project Risks
Scope Creep
Feature requests beyond MVP
High
Mitigation: Clear requirements, change process
Timeline Delays
Development behind schedule
Medium
Mitigation: Buffer time, agile approach
Team Availability
Key team member unavailability
Medium
Mitigation: Cross-training, documentation
Risk Mitigation Strategy
Early Detection
Regular monitoring & reviews
Prevention
Best practices & planning
Mitigation
Backup plans & alternatives
Adaptation
Agile response to changes

## Slide 10
Success Metrics & KPIs
Technical KPIs
Launch time:
< 3s
API response:
< 2s
Crash rate:
< 1%
Test coverage:
> 80%
Uptime:
> 99.5%
Business KPIs
Downloads (Month 1):
1,000+
DAU (Month 3):
500+
Retention (30d):
60%
App Store rating:
> 4.0
Feature adoption:
70%
UX KPIs
Task completion:
> 90%
User error rate:
< 5%
Session duration:
> 5min
NPS Score:
> 50
Satisfaction:
> 4.2/5
Long-term Roadmap
1
Year 1
• Advanced reporting
• Time tracking
• Gantt charts
• Custom fields
2
Year 2
• Web application
• Desktop apps
• Project templates
• Enterprise features
3
Year 3
• AI recommendations
• Voice commands
• AR/VR collaboration
• Advanced automation
Ready to Start
16 weeks to MVP
Strong ROI potential
Scalable architecture